## Adoption Tracker
Adoption Tracker — <Product / Process>
Phase 4–5 · measure OUTCOMES: adoption, tasks completed, hours saved · update weekly during rollout, monthly after
TARGETS (edit yellow)
Target user population | 50 | people
Target adoption rate | 80% | %
Target active users |  | people
Target date | 2026-12-31
Date | Active users | Adoption % | Tasks completed | Hours saved (actual) | Notes
2026-10-05 | 15 |  | 320 | 8 | Rollout wave 1
2026-10-12 | 22 |  | 510 | 14 | Wave 2
2026-10-19 | 28 |  | 690 | 21
2026-10-26 | 34 |  | 850 | 27 | Steady ramp

## Guide
How to use the Adoption Tracker
Active user | Someone who actually used the automation at least once in the period (define per product; use system logs, not surveys).
Adoption % | Active users ÷ target population (auto). Compare against the target rate; green ≥ target, red < 70% of target.
Hours saved (actual) | From logs or time samples. Estimates belong in the business case; the tracker holds ACTUALS only.
Data sources | Product analytics, bot/workflow run logs, helpdesk tickets. If a metric has no data source, mark it and flag in steering.
Cadence | Weekly during rollout/hypercare, monthly after. Two consecutive periods below target → escalate to steering (Gate 5 risk).
Linkage | Adoption numbers feed the steering 1-pager metrics table and the Benefit Realization Tracker.