## Benefits
Benefit Realization Tracker — <Project>
Phase 5 · planned vs ACTUAL benefits, quarterly after go-live · baseline must predate deployment · actuals from systems, not estimates
Benefit | Metric | Unit | Baseline (before) | Planned target | Target date | Q1 actual | Q2 actual | Q3 actual | Q4 actual | % of plan | Status | Direction | Owner / notes
Hours saved | Hours saved per month | h/mo | 0 | 312 | 2027-03-31 | 180 | 260 |  |  |  |  | higher | From bot logs; verify with process owner
Cycle time | Invoice processing time | min/task | 15 | 6 | 2027-03-31 | 9 | 7 |  |  |  |  | lower | From process metrics
Error rate | Rework share | % | 12% | 3% | 2027-03-31 | 6% | 4% |  |  |  |  | lower | Quality KPI
Adoption | Active users | people | 0 | 40 | 2027-03-31 | 22 | 34 |  |  |  |  | higher | From adoption tracker
Cost per transaction | Processing cost | $ | 2.5 | 1.1 | 2027-03-31 | 1.8 | 1.4 |  |  |  |  | lower | Finance data

## Guide
How to use the Benefit Realization Tracker
Baseline rule | Baseline (before) must predate deployment. No baseline = no credible claim (org standard).
Actuals only | Quarterly cells hold ACTUAL measured values from systems — never estimates. Estimates live in the business case; this tracker proves or disproves them.
% of plan | Auto: latest actual ÷ planned target. Direction matters — set Direction to 'higher' (more is better, e.g. hours saved) or 'lower' (less is better, e.g. cycle time, error rate).
Status | Auto: ≥90% On track · 70–89% Behind · <70% At risk.
Cadence | Update quarterly after go-live; feed the steering 1-pager financials table. Benefits re-validated against the business case every quarter.
Honesty rule | Unachieved benefits are reviewed and explained, not hidden. A missed target with a cause beats a hidden one every time.
Linkage | Hours saved here converts to $ via the ROI model hourly rate; adoption comes from the Adoption Tracker.