# Enterprise PO Operating Model — Gate Structure

Refined decision rights: EPO recommends, Sponsor decides. No one approves their own proposal.

## Process Flow (§2)

Phase 0 → G1 (EPO recommends → Sponsor prioritizes) → Phase 1 → G2 (EPO recommends → Sponsor decides Go/No-Go) → Phase 2 → G3 → Phase 3 Delivery → G4 → Phase 4 Adoption → G5 → Phase 5 Value (recurring)

## G1 — Priority Checkpoint (Phase 0: Intake & Triage)

| Role | Detail |
| --- | --- |
| EPO prepares | Triage summary with priority ranking based on portfolio fit, urgency, strategic alignment, rough economics, and blocker check |
| Sponsor decides | Which tasks proceed to Phase 1 discovery and in what priority order |
| Output | Signed priority queue — approved tasks with clear order of execution |

## G2 — Go/No-Go (Phase 1: Discovery & Business Case)

| Role | Detail |
| --- | --- |
| EPO prepares | Complete business case covering: • Feasibility assessment (technical, operational, regulatory) • Total cost estimate (build/buy/configure + running) • Value quantification (hours saved, cost reduction, risk reduction) • ROI model (payback period, break-even, 3-yr ROI) • Proposed solution outline (what, how, by whom) • Risk assessment and mitigation approach |
| Sponsor decides | Go — approve budget, authorise Phase 2 solution selection OR No-Go — kill or defer the project (rationale recorded in decision log) |
| Output | Signed business case with Go/No-Go decision recorded in the decision log |

## Decision Rights Table (§4)

| Decision | Who Prepares | Who Decides | When |
| --- | --- | --- | --- |
| G1: Priority Checkpoint | EPO (triage + priority ranking) | Sponsor | End of Phase 0 |
| G2: Go/No-Go | EPO (business case) | Sponsor | End of Phase 1 |
| G3: Delivery go-ahead | EPO | Sponsor + Architecture review | End of Phase 2 |
| G4: Go-live | EPO | Sponsor + Operations | End of Phase 3 |
| G5: Value review & handover | EPO | Sponsor | End of Phase 4 |
| Quarterly value review | EPO (benefit tracker) | Sponsor | Quarterly in Phase 5 |

## Design Principle

EPO prepares the recommendation and evidence. Sponsor makes the call. No one approves their own proposal.

## Core Accountabilities (§1)

Opportunity framing and business case (economics first)

Gate recommendation preparation — produces the analysis and proposal; does not approve own recommendation

Stakeholder and sponsor management

Requirements and solution ownership (build / buy / configure)

Delivery governance (with delivery leads/PMs where they exist)

Adoption and change — where most value is won or lost

Value measurement and reporting after go-live

## Value & Measurement Standards (§5)

ROI basis (confirm): 1 FTE = 2,080 h/yr; fully loaded $36k/yr

Measure outcomes (hours saved, cycle time, error rate, cost per transaction, capacity freed), not activity

Baselines captured before deployment; benefit claims require before/after evidence

Every business case states: expected payback period, break-even trigger, and kill/stop criteria

Every Go/No-Go decision recorded in decision log with rationale; No-Go decisions preserved for future reference