## RACI
RACI Matrix — <Project>
R = responsible (does the work) · A = accountable (final say, one per row) · C = consulted (input before) · I = informed (told after)
Activity | Sponsor | EPO | Delivery lead | Architecture | Security/Compl | Finance | Procurement | Process owner | Comms/HR | Users
Business case & funding (G2) | A | R | C | C | I | C | I | C | I | I
Solution selection (build/buy/configure) | A | R | C | C | C | C | C | C | I | I
PRD approval | A | R | C | C | C | I | I | C | I | C
Vendor selection & contract | A | R | C | C | C | C | R | C | I | I
Delivery execution | I | A | R | C | C | I | I | C | I | C
UAT sign-off | I | A | R | I | C | I | I | C | I | R
Go-live decision (G4) | A | R | C | C | C | I | I | C | I | I
Training & comms | I | A | C | I | I | I | I | C | R | I
Adoption & value review (G5) | A | R | C | I | I | C | I | C | I | C
Benefits reporting | I | R | I | I | I | C | I | C | I | I

## Guide
How to use the RACI Matrix
Definitions | R = does the work · A = accountable, final say (ONE per row — if two As, the decision is not defined) · C = consulted before the action · I = informed after.
Rules | Exactly one A per row. A and R can be the same person for small items, but for gates they should differ (A = sponsor, R = EPO). Conflict → escalate to sponsor.
Cadence | Build in Phase 1; review at every gate. If a row has no R or no A, that activity is not owned.
Linkage | RACI feeds the decision rights table (Workshop 3) and the comms plan (who to inform).