## RAID Log
RAID Log — <Project / Team>
Risks · Assumptions · Issues · Dependencies — update weekly · top 3 risks/issues feed the steering 1-pager · decisions made here go to the Decision Log
Type | ID | Title / description | Owner | Raised | Status | RAG | Impact (1–5) | Probability (1–5) | Exposure | Mitigation / action plan | Target date | Notes
R | R-001 | Vendor delivery slips on core integration | EPO / Vendor mgr | 2026-09-17 | Open | Red | 4 | 3 |  | Weekly vendor checkpoint; fallback to in-house integration | 2026-12-15
A | A-001 | In-house team has capacity for UAT in Q4 | EPO | 2026-09-17 | Open | Yellow |  |  |  | Confirm staffing with delivery lead in November | 2026-11-20
I | I-001 | Licensing cost overrun on platform seats | EPO / Procurement | 2026-09-17 | Mitigating | Yellow | 3 |  |  | Renegotiate tier; reduce seat count by 15% | 2026-10-31
D | D-001 | Security review sign-off before go-live | Security / EPO | 2026-09-17 | Monitoring | Yellow |  |  |  | Schedule review 4 weeks before go-live | 2026-12-01

## Legend & Guide
RAID definitions
R — Risk | Something that may happen in the future and hurt the project. Has probability + impact. Manage with mitigation.
A — Assumption | Something believed to be true without proof. Validate it — an invalid assumption becomes a risk or issue.
I — Issue | Something that has already happened and needs action now. Owner + target date required.
D — Dependency | Something the project depends on (another team, vendor, system, decision). Track owner and date.
Exposure scoring
Exposure
Cadence & rules
Update weekly | EPO reviews the log weekly; top 3 risks/issues feed the steering 1-pager monthly.
Status transitions | Open → Mitigating/Monitoring → Resolved (or Closed). Never delete rows — history matters.
Decisions | When a RAID item triggers a decision, record it in the Decision Log.
Ownership | Every item has exactly one owner. No owner = item not tracked.