## Scorecard
Vendor Comparison Scorecard — <Requirement>
Phase 2 · weighted criteria · score 1–5 per vendor · weighted total (max 5) · top 2 go to PoC
Criterion | Weight | Vendor A | Vendor B | Vendor C | Notes / evidence
Functional fit | 15% | 4 | 3 | 2 | Score against RFI requirements
TCO 3-yr (higher score = lower cost) | 15% | 3 | 4 | 5 | From vendor pricing + internal effort
Integration capability | 10% | 4 | 3 | 2 | APIs, connectors, data exports
Implementation effort | 10% | 4 | 3 | 3
Support & SLAs | 8% | 3 | 4 | 3
Security & compliance | 12% | 4 | 5 | 4 | Certifications (ISO, SOC2), data residency, EU AI Act posture
Vendor stability & roadmap | 8% | 3 | 4 | 5
References / customer success | 10% | 4 | 3 | 2 | Call 2 references per shortlisted vendor
Training & change support | 7% | 3 | 4 | 2
Contract flexibility | 5% | 3 | 4 | 3 | Terms, exit clauses, pricing model
Weighted total | 100% |  |  |  | Highest = shortlist leader
Rank
PoC shortlist |  |  |  |  | Top 2 go to PoC (poc-evaluation.md)

## Guide
How to use the Vendor Scorecard
Scoring | 1 = poor / no fit · 5 = excellent. Score vendors AFTER the RFI responses, using evidence, not marketing.
TCO criterion | Score is inverse to cost: cheapest TCO scores 5. Collect pricing separately; do not blend raw $ into the score.
Who scores | EPO + procurement + solution architect + process owner, independently, then average. Disputes > 1 point → discuss with evidence.
Shortlist | Top 2 by weighted total go to PoC. Never PoC 3+ vendors — effort explodes, decisions blur.
Compliance first | If a vendor fails security/compliance or data-residency checks, they are out regardless of score (veto criterion).
Decision | PoC results + reference calls + commercial negotiation inform the final choice at Gate 3. Log it in the Decision Log.